## Notes
Group members are responsible for completing and uploading their own timesheets.
You will lose individual marks for each timesheet tab that is not updated on time. |  |  | PRJ566 Winter 2019
Times posted for a specific period should not be modified at a later date.
Must be completed no later than 6:00pm
All sections of this form are mandatory. (please don't modify this form)
Date | See Dates
Activity | A brief description of each task worked on |  | 2019-01-21
Status | Enter "complete" or "in-progress" |  | 2019-01-28
Time spent | A reasonable number of minutes - recording time spent without having |  | 2019-02-04
| something to show for it will result in a major penalty. |  | 2019-02-11
2019-02-17
2019-02-25
|  | Please do not modify the font size on any of the tabs | 2019-03-11
2019-03-18
|  | Always save the worksheet with this tab showing | 2019-03-25
2019-04-01
2019-04-08

## Jan-21
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 2019-01-27
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-01-22 | Researched on which JS Framework and server language to used for website | In Progress | 30
2019-01-24 | Created group email distribution list on Outlook | Complete | 15
2019-01-27 | Worked on Final Document 1.4 Document Purpose and 1.5 Intended Audience | Complete | 30
2019-01-27 | Reviewed Final Document | Complete | 30
| Total for this period |  | 1.75
Do not modify this cell

## Jan-28
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 2019-02-04
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-01-31 | Learned to use MS Project | Complete | 30
2019-01-31 | Research on stackholders, business opportunity and risks | Complete | 30
2019-02-02 | Worked on Final document Section 2.03, 2.05, 2.06 and 2.08 | Complete | 60
2019-02-03 | Reviewed the Final Document | Complete | 30
| Total for this period |  | 2.5
Do not modify this cell

## Feb-04
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 2019-02-10
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-02-07 | Brainstrom all the dataflow diagrams to be made on the Project | Complete | 30
2019-02-09 | Created User and Admin edit profile data flow diagram | Complete | 40
2019-02-10 | Created Quote reminder data flow diagram | Complete | 40
2019-02-10 | Business rules related to Edit Profile and Quote reminder | Complete | 15
2019-02-10 | Reviewed Final Document | Complete | 15
| Total for this period |  | 2.3333
Do not modify this cell

## Feb-11
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 2019-02-17
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-02-16 | Created Use Case Diagram | Complete | 30
2019-02-17 | Updated MS Project assignee to individual and Final Document Links | Complete | 20
2019-02-17 | Reviewed the final document | Complete | 20
| Total for this period |  | 1.1667
Do not modify this cell

## Feb-17
See notes sections
PRJ666 - Timesheet - Group 5
Posted On: | 2019-02-25
Name: | PRATIK PANCHANI
Time spent
Date | Activity/Task | Status | (in minutes)
2019-02-22 | Reviewed Use Case Specification | Complete | 30
| Total for this period |  | 0.5
Do not modify this cell

## Feb-25
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 3/9/2019 - For the week of 4th March
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-03-07 | Solved ROI for Exercise 1 | Complete | 30
2019-03-09 | Admin and User Profile User case Specification | Complete | 40
2019-03-09 | Customize reminder setting User case specification | Complete | 30
2019-03-10 | Reviewed Final Document | Complete | 15
| Total for this period |  | 1.9167
Do not modify this cell

## Mar-11
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 2019-03-18
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-03-15 | Sign In and Sign Out and Forgot Password Use case specification | Complete | 60
2019-03-17 | ROI Exercise 3 | Complete | 30
2019-03-17 | Reviwed Final Document | Complete | 30
| Total for this period |  | 2
Do not modify this cell

## Mar-18
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 2019-03-25
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-03-22 | Researched and Learned MongoDB queries | Complete | 40
2019-03-23 | Completed populate table scipts | Complete | 60
2019-03-24 | Reviewed Final Document | Complete | 20
| Total for this period |  | 2
Do not modify this cell

## Mar-25
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 2019-04-01
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-03-30 | Worked on Acceptance Criteria part of final document | Complete | 30
2019-03-30 | Prepared and researched for giving in class presentation (Design Part) | In Progress | 60
2019-03-31 | Final Document changes - Business Rules, Revision History and others | Complete | 60
2019-03-31 | Reviewed other parts of the final document before submission | Complete | 30
| Total for this period |  | 3
Do not modify this cell

## Apr-01
See notes sections
PRJ666 - Timesheet - Group 05
Posted On: | 2019-04-07
Name: | Pratik Panchani
Time spent
Date | Activity/Task | Status | (in minutes)
2019-04-01 | Created slides for presenting user interface(Sample Mockups) and design part | Complete | 90
2019-04-02 | Reviewed final overall presentation | Complete | 30
2019-04-03 | Prepeared for the presentation speech | Complete | 60
| Total for this period |  | 3
Do not modify this cell

## Apr-08
A
See notes sections
PRJ666 - Timesheet - Group _______
Posted On:
Name:
Time spent
| Date | Activity/Task | Status | (in minutes)
|  | Total for this period |  | 0
Do not modify this cell

## Total
See notes sections
PRJ666 - Timesheet - Group _______
Posted On:
Name:
Time spent
| Running Total | 20.1667
Do not modify this cell